## Slide 1
Current Schedule of Work Plan*
Units / Flat Still To be Scheduled
A - commercial
B - commercial
C - commercial
Apartments CURRENTLY NOT Requiring Firestopping (Apart from Remediation to Front Doors) |  |  |  | 
3 | 5 | 7 | 19 | 22
23 | 30 | 31 | 33 | 44
46 |  |  |  | 
1
2
3
This schedule is subject to current plans / work by apartment
# 1st May = Bank Holiday
Keystone Contacted (ing) to Confirm Days |  |  |  | Provisional - Keystone To Make Contact Next Week to Confirm Days |  |  |  |  |  | 
W/C 24th April 2023 |  | W/C 2nd May 2023 # |  | W/C 8th May 2023 |  | W/C 15th May 2023 |  | W/C 22nd May 2023 |  | W/C 29th May 2023
1 |  | 16 |  | 21 |  | 4 |  | 22 |  | 14
2 |  | 28 |  | 23 |  | 9 |  | 48 |  | 36
3 |  | 29 |  | 24 |  | 11 |  | 49 |  | 37
5 |  | 32 |  | 25 |  | 12 |  |  |  | 39
6 |  | 34 |  | 26 |  | 15 |  |  |  | 43
7 |  | 38 |  | 27 |  | 17 |  |  |  | 44
8 |  | 42 |  | 31 |  | 18 |  |  |  | 45
10 |  | 47 |  | 33 |  | 19 |  |  |  | 46
30 |  |  |  | 40 |  | 20 |  |  |  | 
35 |  |  |  |  |  |  |  |  |  | 
41 |  |  |  |  |  |  |  |  |  |